## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43297 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
First Semester Report | 2018-07-16 | 2018-07-20 | 5 | 3 | 1 | 75%
Learn PIC32 | 2018-07-23 | 2018-07-27 | 5 | 0 | 4 | 0%
Learn ESP8266 | 2018-07-23 | 2018-07-27 | 5 | 0 | 4 | 0%
Interface PIC32 with ESP8266 WiFi module | 2018-07-23 | 2018-08-03 | 12 | 0 | 11 | 0%
Interface Temperature Sensor with PIC32 | 2018-07-23 | 2018-08-03 | 12 | 0 | 11 | 0%
Interface ESP8266 via WiFi with PC | 2018-07-23 | 2018-07-27 | 5 | 0 | 4 | 0%
Design and Implement Sensor Filters | 2018-08-06 | 2018-08-08 | 3 | 0 | 2 | 0%
Implement Sensor Node on Veroboard | 2018-08-06 | 2018-08-10 | 5 | 0 | 4 | 0%
Get Training Data | 2018-08-13 | 2018-08-24 | 12 | 0 | 11 | 0%
Background Study on Feed-Forward Neural Networks | 2018-08-13 | 2018-08-17 | 5 | 0 | 4 | 0%
Background Study on Neural Network Trainnig Methods | 2018-08-13 | 2018-08-17 | 5 | 0 | 4 | 0%
Design and Implement and Simulate Neural Network on PC Using Dummy Data | 2018-08-20 | 2018-08-24 | 5 | 0 | 4 | 0%
Implement and Train Neural Network on PC Using Sensor Data | 2018-08-27 | 2018-08-31 | 5 | 0 | 4 | 0%
Implement Neural Network on a Sensor Node | 2018-09-03 | 2018-09-07 | 5 | 0 | 4 | 0%
Test Sensor Nodes with Neural Network in Environment | 2018-09-10 | 2018-09-21 | 12 | 0 | 11 | 0%
Get Results For Report | 2018-09-10 | 2018-09-21 | 12 | 0 | 11 | 0%
Write Final Report | 2018-09-23 | 2018-11-01 | 40 | 0 | 39 | 0%
Miscellaneous Additions if Enough Time | 2018-09-23 | 2018-11-01 | 40 | 0 | 39 | 0%
Practice Oral for Final Exam | 2018-10-15 | 2018-11-01 | 18 | 0 | 17 | 0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.